## Slide 1: KITE Project Review – February 2020

## Slide 2: Agenda
Summary of Activities
Project Status – Content builder
  Offshore – QA Activities

## Slide 3: Summary of Activities
Activities
Editor Tool for CB 2.0 – Analysis and POC
  Tiny Text Editor
  Shield UI Editor
  Kendo UI Editor
Workflow Tools for CB 2.0 – Analysis and POC
  Activity Workflow
  Flowable Workflow
  DLM Acapella tagging dictionary for Polly
  Analyzing the new rule for words which is equivalent to acapella words.
React Js
  Walkthrough on Basics of React Library
  Analysis on React Components.
  ES5 and ES6 Features.

## Slide 4: Content Builder
Green
5 Dev + 2 QA
CB 2.0 tools analysis
Overall Status
Team

## Slide 5
Content Builder
Task | Features | Start Date | End Date | % of Completion | Planned Effort (in hrs.) | Actual Effort (in hrs.) | RAG | Comment
 | Text Editor Analysis & POC | 29-Jan-20 | 18-Feb-20 | 100% | 25 | 25 | G | CK-Editor4 is chosen
 | Workflow Analysis & POC | 28-Jan-20 | 17-Feb-20 | 100% | 52 | 49 | G | 
 | DLM Acapella tagging dictionary for Polly | 11-Feb-20 | 12-Feb-20 | 82% | 85 | 70 | G | In-Progress(Planned to release this as patch)
 | Regression and Production Defects fixing | 07-Feb-20 | 19-Feb-20 | 100% | 65 | 65 | G | DE20500, DE20510, DE20512
 | React Js(UI Design) Walkthrough | 29-Jan-20 |  |  |  |  | G | Started Looking on React basics.
Status as of 25-Febraury-2020, 16:00 hours IST

## Slide 6
Content Builder QA –Activity
Task | Features | Start Date | End Date | % of Completion | Planned Effort (in hrs.) | Actual Effort (in hrs.) | RAG | Comment
QA | Regression Testing & Defects Validation | 29-Jan-19 | 20-Feb-20 | 100% | 128 | 128 | G | Verified & Closed the defects DE19169, DE20439, DE20500, DE20205, DE20509, DE20510, DE20512 in QA & Stage environment
QA | CB 2.0 Analysis & Understanding | 03-Feb-20 | 21-Feb-20 | 100% | 47 | 47 | G | 
QA | Polly Misspelled Words & Pronunciation Issue Analysis | 10-Feb-20 | 12-Feb-20 | 100% | 26 | 26 | G | 
QA | F1073 : QTI Redesign - UAT Walk Through | 13-Feb-20 | 13-Feb-20 | 100% | 1 | 1 | G | 
QA | Post Production activities for Height Release deployment | 21-Feb-20 | 21-Feb-20 | 100% | 10 | 10 | G | 
Status as of 25-February-2020, 16:00 hours IST.
Apart from the above activities QA had started analyzing on Automation tools like Selenium and VIP Test Modeller (Visual Integration Processor) and will continue to work on the same.

## Slide 7: CB 2.0 Summary
Text Editor Analysis:
Analyzed different types of editors and checked how far that editor is suitable for CB Application.
Created POC by using those editors in React.
CKEditor 5 in React
Shield UI Editor in React
Kendo UI Editor - Analysis
And also we evaluated licensing and pricing provided by Tiny MCE 5 for Cloud based and self hosted.
Workflow Analysis:
Done POCs in Activiti and flowabe for checking supported BPMN 2.0 events and notifications.
Based on the provided requirements like skip a workflow step and repeating a workflow step, analyzed whether it can be done in Activiti and Flowable.
We also found one of the requirement is not supporting in activiti, so we decided to proceed only with flowable.
Did POC's using Skip Workflow and repeating workflow with the help of database configurations.
Analyzed further in flowable like audit logs and prepared documentation based on our analysis against the given requirement
Analyzed Flowable default functions and auto created DB tables which can be useful against our requirements..
Updated and shared the document with complete analysis on what we can do with flowable.

## Slide 8: CB 2.0 Summary
React JS :
Walkthrough on basic react library classes and functions.
Understanding react components(Class Component and Functional Component).
Understanding the concepts of React Lifecycle.
Analysis on ES5 and ES6 concepts(Which help us to improvise our UI implementation using React).
Analysis on Hooks concepts and Usages(How to make out functional component as state-full).
Understanding Redux usages(State management in React).
Did POC's on Text Editor using React Library.
Did small POC on Authentication using JWT with Spring Boot and React(Connect both React and Java).

## Slide 9: Thank You